## Sheet1
FER on Music Recommendation System
Yie Nian Chu 21061710
| 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13
TASK | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32
Planning, Design and Research
Research | bar: 2023-10-09 to 2023-10-16
Project Proposal | bar: 2023-10-16
Data Collection | bar: 2023-10-16 to 2023-10-23
Design Web Application Structure | bar: 2023-10-16 to 2023-10-23
Decide Framework | bar: 2023-10-16 to 2023-10-23
Create UML Diagrams | bar: 2023-10-23 to 2023-10-30
Create Test Plan | bar: 2023-10-23 to 2023-10-30
Machine Learning Model Development
Train initial model | bar: 2023-11-06 to 2023-11-27
Evaluate initial model | bar: 2023-11-20 to 2023-12-11
Train enhanced model | bar: 2023-11-27 to 2024-01-29
Evaluate enhanced model | bar: 2023-12-11 to 2024-01-01
Web Application Development
Database Setup | bar: 2023-11-27
Implement user authentication (REQ. FUNC. 1~3) | bar: 2023-12-04 to 2023-12-18
Implement user settings (REQ. FUNC. 4~5) | bar: 2023-12-11 to 2023-12-25
Implement Spotify API authentication (REQ. FUNC. 8) | bar: 2023-12-18 to 2024-01-01
Implement Spotify API integration (REQ. FUNC. 7) | bar: 2023-12-25 to 2024-01-29
Implement music recommendation system (REQ. FUNC. 9) | bar: 2024-01-08 to 2024-01-15
Implement multi-languages support (REQ. FUNC. 11) | bar: 2024-01-08 to 2024-01-15
Implement theme swtiching (REQ. FUNC. 10) | bar: 2024-01-22
Implement machine learning integration (REQ. FUNC. 6) | bar: 2024-01-22
Testing | bar: 2024-02-05 to 2024-02-26
Testing initial model accuracy | bar: 2023-11-20 to 2023-12-04
Testing enhanced model accuracy | bar: 2023-12-11 to 2023-12-18
Testing user authentication system | bar: 2023-12-18
Testing user profile settings | bar: 2023-12-18 to 2023-12-25
Testing Spotify Web Playback | bar: 2024-01-01 to 2024-01-29
Identify security risks | bar: 2024-03-04 to 2024-03-11
Identify performance issues | bar: 2024-03-04 to 2024-03-11
Testing machine learning integration | bar: 2024-03-18 to 2024-03-25
Documentation
Writing report | bar: 2024-03-04 to 2024-05-06
Demostration and presentation | bar: 2024-05-13